FestivalAI

Production Process

Dinesh Sivakumar  |  AI Video Specialist

Project Objective

FestivalAI was developed to explore how AI-assisted creative workflows can be used to produce culturally localized marketing campaigns for different Indian festivals and regional audiences. The project focused on creating multilingual campaigns for Diwali (Hindi), Pongal (Tamil), Onam (Malayalam), and Durga Puja (Bengali).

Pipeline Overview

Phase 1: Research  →  Phase 2: Script  →  Phase 3: Storyboard  →  Phase 4: Visuals  →  Phase 5: Voice-Over  →  Phase 6: Editing  →  Phase 7: Delivery

Phase 1  Research & Concept Development

The production process began with researching the cultural significance, traditions, and audience expectations for each festival. This grounding phase ensured every creative decision was rooted in regional authenticity rather than generic assumptions.

Key research areas:

- Festival customs, traditions, and symbolic objects specific to each region

- Regional language preferences and tone of communication

- Visual aesthetics — colours, attire, architecture, and setting per festival

- Family and community themes that resonate with each audience

- Audience engagement factors and platform behaviour for digital content

Based on this research, a unique campaign concept was developed for each festival before any content was created.

Phase 2  Script Development

Story narratives were written to align with the cultural context of each festival. Scripts were not translated versions of a single master — each was written independently to feel native to its language and audience.

Each script was structured around:

- Emotional storytelling — a clear arc from opening hook to resolution

- Family and community connections relevant to the festival

- Celebration moments that capture the mood and spirit of the occasion

- Regional relevance — references, phrases, and tone natural to each language

- Audience engagement — pacing and language designed for short-form digital content

Scripts were then adapted to their respective languages — Hindi, Tamil, Malayalam, and Bengali — before moving to storyboarding.

Phase 3  Storyboard Creation

Before generating any visual content, detailed storyboards were created for each campaign. This step translated the written script into a visual plan — defining exactly what would appear on screen, scene by scene.

Each storyboard defined:

- Scene structure — number of scenes, duration, and story beat per scene

- Character actions — what characters are doing, expressing, and feeling in each shot

- Visual composition — framing, foreground/background elements, festival props

- Narrative flow — how scenes connect and build emotional momentum

- Transition planning — how the story moves from one scene to the next

Storyboarding before generation was critical — it served as the brief for every AI-generated visual asset and kept the campaign consistent from first frame to last.

Phase 4  Visual Asset Generation

With storyboards as the creative brief, AI-assisted tools were used to generate visual assets for each scene. Every asset was generated with cultural specificity in mind — not generic festival imagery, but visuals grounded in the research from Phase 1.

Visual assets generated included:

- Festival-specific environments — Pongal courtyards, Diwali-lit homes, Onam flower arrangements, Durga Puja pandals

- Character-focused scenes — families, expressions, and cultural attire accurate to each region

- Celebration moments — fireworks, diyas, pookalam, sugarcane — festival symbols specific to each campaign

- Cinematic visual compositions — framing and lighting designed to feel like a produced ad, not a generic AI clip

Multiple iterations were explored per scene to achieve the right visual quality, cultural accuracy, and storytelling impact before assets were approved for editing.

Phase 5  Voice-Over Production

Voice-over narration was produced in the native language of each campaign — Hindi, Tamil, Malayalam, and Bengali. AI voice generation tools were used to create natural-sounding narration that matched the emotional tone of each story.

Voice-over production focused on:

- Language accuracy — narration written and generated in each campaign's native language

- Emotional tone — pacing and delivery matched to the mood of each scene

- Story support — voice-over designed to enhance the visual narrative, not just describe it

- Audio quality — clean output suitable for synchronization with video content

This phase eliminated the need for regional voice artists while maintaining language authenticity across all four campaigns.

Phase 6  Video Production & Editing

All visual assets and voice-over tracks were assembled into final videos using CapCut and Filmora. This was the stage where all elements came together — the story, the visuals, the voice, and the pacing — into a cohesive campaign video.

Editing activities included:

- Scene sequencing — arranging visual assets in storyboard order to build the narrative arc

- Audio synchronization — aligning voice-over narration with corresponding visuals frame by frame

- Transition design — smooth, culturally appropriate transitions between scenes

- Timing adjustments — pacing refined to match platform requirements for short-form digital content

- Final composition — colour correction, audio balancing, and export optimization for social media and digital platforms

Phase 7  Final Campaign Delivery

Completed campaigns were reviewed against the original story concept and cultural brief, then exported as final promotional videos ready for digital distribution.

Final deliverables per campaign:

- Storyboard document — scene-by-scene visual plan

- Generated visual assets — individual scene images and compositions

- Voice-over narration — final audio track in native language

- Final marketing video — edited, colour-corrected, and platform-optimized promotional video

Project Outcomes

- Produced 4 complete multilingual festival marketing campaigns

- Created content for Hindi, Tamil, Malayalam, and Bengali-speaking audiences

- Demonstrated AI-assisted storytelling and content production workflows

- Showcased end-to-end ownership from concept development to final video delivery

- Established a repeatable 7-phase process for localized marketing campaign creation

Tools Used

AI Tools: ChatGPT, Qwen, Microsoft Copilot, Seedance, Arena,ComfyUi,Higgsfield

Creative & Video Tools: CapCut, Filmora, Pixabay